## Settings
Gantt
Project Details |  |  | Project Role Types |  |  |  | Project Role Types |  |  |  | Holidays
| Project Title: | Apache Webservicemix ESB |  | Role | Code: | # |  | Name | Role | Code |  | Event | Date (ddd-mm-jjjj)
|  |  |  | Delivery Director | DD | 1 |  | Jeff Schappert | Delivery Director | DD |  |  | 2024-04-09
| Delivery Manager: | Dilip Kumar |  | Delivery Lead | DL | 1 |  | Dilip Kumar | Delivery Lead | DL |  |  | 2024-04-10
|  |  |  | EA interface Architect | EA | 1 |  | Steve Weiland | EA interface Architect | EA |  |  | 2024-05-01
| Project Priority: | High |  | ESB Service Mix Config SE | ESBCSE | 3 |  | Sawan Kumar | ESB Service Mix Config SE | ESBCSE |  |  | 2024-08-15
|  |  |  | ESB Service Mix Lead | ESBL | 1 |  | Sateesh Kumar | ESB Service Mix Lead | ESBL |  |  | 2024-09-06
|  |  |  | Business Analyst | BA | 1 |  | Dhananjay Kumar | ESB Service Mix Config SE | ESBCSE |  |  | 2024-10-02
|  |  |  | Quality Assurance Lead | QAL | 1 |  | Kolli Srinivas Rao | ESB Service Mix Config SE | ESBCSE |  |  | 2024-10-31
|  |  |  | Cloud Architect | CA | 1 |  | Guru Theja Ganta | Quality Assurance Lead | QAL
|  |  |  | Quality Assurance | QA | 2 |  | Akhil Nayak | Quality Assurance | QA
|  |  |  | Test Data Engineer | TDE | 1 |  | Dimple HG | Quality Assurance | QA
[8 empty] | Kranthi Kumar | Business Analyst | BA
[8 empty] | Sudhindra S | Cloud Architect | CA
[8 empty] | Sharad Nagesh | Test Data Engineer | TDE

## Gantt
Apache Webservicemix ESB | [19 empty] | Project Timespan | [5 empty] | 2024-01-29 | [5 empty] | - | 2024-08-09 | [5 empty] | (140) |  |  | Delivery Manager: | [6 empty] | Dilip Kumar | [10 empty] | Settings
| insert column | [18 empty] | Color by | [7 empty] | Display | [6 empty] | Show progress | [25 empty] | Highlight
| calculated column | [18 empty] | Project Structure | [7 empty] | Plan vs Base | [6 empty] | No | [25 empty] | Today
snapshot column
⚠ -⬥- ↖ - ↙ - O | [7 empty] | Actual Plan | [8 empty] | Base Plan |  | Today | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-02 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-13 | 2024-03-14 | 2024-03-15 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04
[8 empty] | update on: | [8 empty] | saved on: |  | 1
ids |  |  | item details |  |  |  |  | 2024-01-28 | [8 empty] | 2024-01-30
id | s id | r id | Type | Description | Role | Team Member | ⚠ | ind. Start | d. id | d. item |  | d. conn | d. lag | Work days | Start | End | Start | End | % | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T
1 | 1 | -1 | S | Sprint 0 |  |  |  | 2024-01-29 | 2 |  | (T)Sprint ... | SF |  | 9 | 2024-01-29 | 2024-02-08 | 2024-01-29 | 2024-02-08 | 24.34% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 2 | T | Sprint planning/ Backlog Refinement | DL | Dilip Kumar |  | 2024-01-29 | 12 |  | (T)Upgrade... | SF |  | 1 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 7 | T | Document current APIs | QAL | Guru Theja Ganta |  | 2024-01-30 | 14 |  | (T)Build E... | SS |  | 2 | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-31 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 6 | T | Architecture Design Document Template | BA | Kranthi Kumar |  | 2024-01-30 |  |  |  | SF |  | 1 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1 | 3 | T | Provisioning Infrastructure | EA | Steve Weiland |  | 2024-01-30 |  |  |  | SS |  | 2 | 2024-01-30 | 2024-01-31 | 2024-01-30 | 2024-01-31 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1 | 5 | T | Review production environment configuration | ESBL | Sateesh Kumar |  | 2024-01-30 |  |  |  | FF |  | 1 | 2024-01-30 | 2024-01-30 | 2024-02-01 | 2024-02-01 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1 | 4 | T | Build Dev and Test environments | ESBCSE | Dhananjay Kumar |  | 2024-02-01 | 5 | ↖ | (T)Provisi... | SS |  | 2 | 2024-02-01 | 2024-02-02 | 2024-02-01 | 2024-02-02 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1 | 7 | T | Identifying bundles to migrates as a pilot | QAL | Guru Theja Ganta |  | 2024-01-30 | 16 |  | (T)Side by... | FF |  | 1 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 1 | 3 | T | Application and environment walkthrough | EA | Steve Weiland |  | 2024-01-30 |  |  |  | SF |  | 1 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 40% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 1 | 7 | T | Design Test Plan for Pilot | QAL | Guru Theja Ganta |  | 2024-01-31 | 12 |  | (T)Upgrade... | SS |  | 1 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 1 | 6 | T | Documentation Standard | BA | Kranthi Kumar |  | 2024-01-31 |  |  |  | FF |  | 1 | 2024-01-31 | 2024-01-31 | 2024-01-30 | 2024-01-30 | 80% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 1 | 4 | T | Upgrade Pilot for SMS Bundle | ESBCSE | Kolli Srinivas Rao |  | 2024-01-30 |  |  |  | SS |  | 5 | 2024-01-30 | 2024-02-05 | 2024-01-31 | 2024-02-06 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | 4 | T | Version 7: requirement gathering and installation | ESBCSE | Sawan Kumar |  | 2024-01-31 | 5 | ↖ | (T)Provisi... | SS |  | 3 | 2024-01-31 | 2024-02-02 | 2024-01-31 | 2024-02-02 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | 7 | T | Build EA view of interface acrhictecture | QAL | Guru Theja Ganta |  | 2024-01-31 | 5 | ↖ | (T)Provisi... | SS |  | 3 | 2024-01-31 | 2024-02-02 | 2024-01-31 | 2024-02-02 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1 | 3 | T | Review ESB Architecture Design | EA | Steve Weiland |  | 2024-01-31 |  |  |  | SS |  | 3 | 2024-01-31 | 2024-02-02 | 2024-01-31 | 2024-02-02 | 12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1 | 4 | T | Side by Side Version comparison | ESBCSE | Dhananjay Kumar |  | 2024-01-30 |  |  |  | SS |  | 8 | 2024-01-30 | 2024-02-08 | 2024-01-30 | 2024-02-08 | 12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | -1 | S | Sprint 1 |  |  |  | 2024-02-29 |  |  |  | SS |  | 18 | 2024-02-29 | 2024-03-25 | 2024-02-29 | 2024-03-25 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | 2 | T | Sprint planning/ Backlog Refinement | DL | Dilip Kumar |  | 2024-02-29 | 20 |  | (T)Applica... | SS |  | 1 | 2024-02-29 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | 8 | T | Set up infrastructure, software and tools | CA | Sudhindra S |  | 2024-02-29 | 20 |  | (T)Applica... | SS |  | 5 | 2024-02-29 | 2024-03-06 | 2024-02-29 | 2024-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | 3 | T | Application discovery (SMS Bundle) | EA | Steve Weiland |  | 2024-02-29 |  |  |  | SS |  | 3 | 2024-02-29 | 2024-03-04 | 2024-02-29 | 2024-03-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | 7 | T | Define test cases | QAL | Guru Theja Ganta |  | 2024-03-05 | 20 | ↖ | (T)Applica... | SS |  | 2 | 2024-03-05 | 2024-03-06 | 2024-03-05 | 2024-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1 | -1 | T | Prepare test data | TDE | Sharad Nagesh |  | 2024-03-06 | 22 | ↙ | (T)Prepare... | SS |  | 3 | 2024-03-06 | 2024-03-08 | 2024-03-06 | 2024-03-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | 4 | T | Upgrade software | ESBCSE | Kolli Srinivas Rao |  | 2024-03-06 |  |  |  | SS |  | 4 | 2024-03-06 | 2024-03-11 | 2024-03-06 | 2024-03-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-03-12 | 19 | ↖ | (T)Set up ... | SS |  | 1 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 1 | 7 | T | Functional test, Issues resolution | QAL | Guru Theja Ganta |  | 2024-03-13 | 24 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-03-13 | 2024-03-14 | 2024-03-13 | 2024-03-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 1 | 4 | T | Parallel test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-03-13 | 23 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-03-13 | 2024-03-18 | 2024-03-13 | 2024-03-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 1 | 5 | T | Integration test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-03-19 | 23 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-03-19 | 2024-03-22 | 2024-03-19 | 2024-03-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 1 | 4 | T | Documentation | ESBCSE | Sawan Kumar |  | 2024-03-18 | 24 | ↖ | (T)Unit Te... | SS |  | 5 | 2024-03-18 | 2024-03-22 | 2024-03-18 | 2024-03-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | 2 | T | Sprint review | DL | Dilip Kumar |  | 2024-03-25 | 27 | ↖ | (T)Integra... | SS |  | 1 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 1 | 6 | T | Sprint retrospective | BA | Kranthi Kumar |  | 2024-03-25 | 27 | ↖ | (T)Integra... | SS |  | 1 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 1 | -1 | S | Sprint 2 |  |  |  | 2024-03-26 |  |  |  | SS |  | 27 | 2024-03-26 | 2024-05-01 | 2024-03-26 | 2024-04-17 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 1 | 2 | T | Sprint planning/ Backlog Refinement | DL | Dilip Kumar |  | 2024-03-26 |  |  |  | SS |  | 1 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 1 | 3 | T | Application discovery (T24DataXFer Bundle) | EA | Steve Weiland |  | 2024-03-26 |  |  |  | SS |  | 3 | 2024-03-26 | 2024-03-28 | 2024-03-26 | 2024-03-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 1 | 7 | T | Define test cases | QAL | Guru Theja Ganta |  | 2024-03-29 | 47 |  | (T)Paralle... | SS |  | 2 | 2024-03-29 | 2024-04-01 | 2024-03-29 | 2024-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 1 | -1 | T | Prepare test data | TDE | Sharad Nagesh |  | 2024-04-03 | 48 |  | (T)Integra... | SS |  | 3 | 2024-04-03 | 2024-04-05 | 2024-04-03 | 2024-04-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 1 | 4 | T | Upgrade Software | ESBCSE | Sawan Kumar |  | 2024-04-02 |  |  |  | SS |  | 4 | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | 5 | T | Unit Test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-04-04 | 36 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-04-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 1 | 7 | T | Functional test, Issues resolution | QAL | Guru Theja Ganta |  | 2024-04-05 | 37 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-04-05 | 2024-04-08 | 2024-04-05 | 2024-04-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 1 | 4 | T | Parallel test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-04-12 | 38 | ↖ | (T)Functio... | SS |  | 4 | 2024-04-12 | 2024-04-17 | 2024-04-05 | 2024-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 1 | 4 | T | Integration test, Issues resolution | ESBCSE | Kolli Srinivas Rao |  | 2024-04-26 | 36 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-04-26 | 2024-05-01 | 2024-04-12 | 2024-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1 | 3 | T | Application discover (APXFer Bundle) | EA | Steve Weiland |  | 2024-03-26 |  |  |  | SS |  | 3 | 2024-03-26 | 2024-03-28 | 2024-03-26 | 2024-03-28 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 1 | -1 | T | Define test cases | QA | Akhil Nayak |  | 2024-03-29 | 41 | ↖ | (T)Applica... | SS |  | 3 | 2024-03-29 | 2024-04-02 | 2024-03-29 | 2024-04-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 1 | -1 | T | Prepare test data | QA | Dimple HG |  | 2024-04-02 | 42 | ↖ | (T)Define ... | SS |  | 3 | 2024-04-02 | 2024-04-04 | 2024-04-02 | 2024-04-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 1 | 4 | T | Upgrade software | ESBCSE | Kolli Srinivas Rao |  | 2024-04-02 |  |  |  | SS |  | 4 | 2024-04-02 | 2024-04-05 | 2024-04-02 | 2024-04-05 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-04-05 | 44 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-04-05 | 2024-04-05 | 2024-04-04 | 2024-04-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 1 | 5 | T | Functional test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-04-05 | 45 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-04-05 | 2024-04-08 | 2024-04-05 | 2024-04-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 1 | 4 | T | Parallel test, Issues resolution | ESBCSE | Sawan Kumar |  | 2024-04-12 | 46 | ↖ | (T)Functio... | SS |  | 4 | 2024-04-12 | 2024-04-17 | 2024-04-05 | 2024-04-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 1 | 4 | T | Integration test, Issues resolution | ESBCSE | Kolli Srinivas Rao |  | 2024-04-11 | 44 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-04-11 | 2024-04-16 | 2024-04-12 | 2024-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 1 | 6 | T | Documentation | BA | Kranthi Kumar |  | 2024-04-11 | 32 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-04-11 | 2024-04-17 | 2024-04-11 | 2024-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 1 | 2 | T | Sprint review | DL | Dilip Kumar |  | 2024-04-17 |  |  |  | SS |  | 1 | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 1 | 3 | T | Sprint retrospective | EA | Steve Weiland |  | 2024-04-17 |  |  |  | SS |  | 1 | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-04-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 1 | -1 | S | Sprint 3 |  |  |  | 2024-04-16 |  |  |  | SS |  | 19 | 2024-04-16 | 2024-05-10 | 2024-04-18 | 2024-05-09 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 1 | 2 | T | Sprint planning/ Backlog Refinement | DL | Dilip Kumar |  | 2024-04-18 |  |  |  | SS |  | 1 | 2024-04-18 | 2024-04-18 | 2024-04-18 | 2024-04-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 1 | 3 | T | Application discover (T24caseware Bundle) | EA | Steve Weiland |  | 2024-04-18 |  |  |  | SS |  | 3 | 2024-04-18 | 2024-04-22 | 2024-04-18 | 2024-04-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 1 | 7 | T | Define test cases | QAL | Guru Theja Ganta |  | 2024-04-23 | 54 | ↖ | (T)Applica... | SS |  | 2 | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-04-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 1 | -1 | T | Prepare test data | TDE | Sharad Nagesh |  | 2024-04-25 | 55 | ↖ | (T)Define ... | SS |  | 3 | 2024-04-25 | 2024-04-29 | 2024-04-25 | 2024-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 1 | 4 | T | Upgrade software | ESBCSE | Sawan Kumar |  | 2024-04-25 |  |  |  | SS |  | 4 | 2024-04-25 | 2024-04-30 | 2024-04-25 | 2024-04-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-04-29 | 57 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-04-29 | 2024-04-29 | 2024-04-29 | 2024-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 1 | 7 | T | Functional test, Issues resolution | QAL | Guru Theja Ganta |  | 2024-04-29 | 58 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-04-29 | 2024-04-30 | 2024-04-30 | 2024-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 1 | -1 | T | Parallel test, Issues resolution | QA | Akhil Nayak |  | 2024-04-30 | 59 | ↖ | (T)Functio... | SS |  | 4 | 2024-04-30 | 2024-05-03 | 2024-04-30 | 2024-05-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 1 | 5 | T | Integration test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-05-06 | 57 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-05-06 | 2024-05-09 | 2024-05-06 | 2024-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 1 | 3 | T | Application discovery (PMB Bundle) | EA | Steve Weiland |  | 2024-04-16 |  |  |  | SS |  | 3 | 2024-04-16 | 2024-04-18 | 2024-04-18 | 2024-04-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 1 | -1 | T | Define test cases | TDE | Sharad Nagesh |  | 2024-04-23 | 62 | ↖ | (T)Applica... | SS |  | 2 | 2024-04-23 | 2024-04-24 | 2024-04-23 | 2024-04-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 1 | -1 | T | Prepare test data | QA | Akhil Nayak |  | 2024-04-25 | 63 | ↖ | (T)Define ... | SS |  | 2 | 2024-04-25 | 2024-04-26 | 2024-04-25 | 2024-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 1 | 5 | T | Upgrade software | ESBL | Sateesh Kumar |  | 2024-04-25 |  |  |  | SS |  | 4 | 2024-04-25 | 2024-04-30 | 2024-04-25 | 2024-04-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Kolli Srinivas Rao |  | 2024-04-25 | 65 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-04-25 | 2024-04-25 | 2024-04-29 | 2024-04-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 1 | 7 | T | Functional test, Issues resolution | QAL | Guru Theja Ganta |  | 2024-04-30 | 66 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-04-30 | 2024-05-01 | 2024-04-30 | 2024-05-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 1 | -1 | T | Parallel test, Issues resolution | QA | Dimple HG |  | 2024-04-30 | 67 | ↖ | (T)Functio... | SS |  | 4 | 2024-04-30 | 2024-05-03 | 2024-04-30 | 2024-05-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 1 | 5 | T | Integration test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-05-06 | 65 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-05-06 | 2024-05-09 | 2024-05-06 | 2024-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 1 | 6 | T | Documentation | BA | Kranthi Kumar |  | 2024-05-06 | 53 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-05-06 | 2024-05-10 | 2024-05-03 | 2024-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 1 | 3 | T | Sprint review | EA | Steve Weiland |  | 2024-05-09 |  |  |  | SS |  | 1 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2024-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 1 | 2 | T | Sprint retrospective | DL | Dilip Kumar |  | 2024-05-09 |  |  |  | SS |  | 1 | 2024-05-09 | 2024-05-09 | 2024-05-09 | 2024-05-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 1 | -1 | S | Sprint 4 |  |  |  | 2024-05-10 |  |  |  | SS |  | 15 | 2024-05-10 | 2024-05-30 | 2024-05-10 | 2024-05-30 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 1 | 2 | T | Sprint planning/ Backlog Refinement | DL | Dilip Kumar |  | 2024-05-10 |  |  |  | SS |  | 1 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 1 | 3 | T | Application discovery (T24InvestmentRelay Bundle) | EA | Steve Weiland |  | 2024-05-10 |  |  |  | SS |  | 3 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 1 | -1 | T | Define test cases | QA | Akhil Nayak |  | 2024-05-15 | 75 | ↖ | (T)Applica... | SS |  | 2 | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 1 | -1 | T | Prepare test data | TDE | Sharad Nagesh |  | 2024-05-17 | 76 | ↖ | (T)Define ... | SS |  | 3 | 2024-05-17 | 2024-05-21 | 2024-05-17 | 2024-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 1 | 5 | T | Upgrade software | ESBL | Sateesh Kumar |  | 2024-05-17 | 75 | ↖ | (T)Applica... | SS |  | 4 | 2024-05-17 | 2024-05-22 | 2024-05-17 | 2024-05-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Kolli Srinivas Rao |  | 2024-05-21 | 78 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 1 | 7 | T | Functional test, Issues resolution | QAL | Guru Theja Ganta |  | 2024-05-22 | 79 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-05-22 | 2024-05-23 | 2024-05-22 | 2024-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 1 | 4 | T | Parallel test, Issues resolution | ESBCSE | Sawan Kumar |  | 2024-05-22 | 78 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-05-22 | 2024-05-27 | 2024-05-22 | 2024-05-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 1 | 5 | T | Integration test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-05-27 | 78 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-05-27 | 2024-05-30 | 2024-05-27 | 2024-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 1 | 3 | T | Application discover (PortfolioManagement Bundle) | EA | Steve Weiland |  | 2024-05-10 |  |  |  | SS |  | 3 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-14 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 1 | 7 | T | Define test cases | QAL | Guru Theja Ganta |  | 2024-05-10 | 83 | ↖ | (T)Applica... | SS |  | 2 | 2024-05-10 | 2024-05-13 | 2024-05-15 | 2024-05-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 1 | -1 | T | Prepare test data | TDE | Sharad Nagesh |  | 2024-05-15 | 84 | ↖ | (T)Define ... | SS |  | 3 | 2024-05-15 | 2024-05-17 | 2024-05-17 | 2024-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 1 | 4 | T | Upgrade software | ESBCSE | Sawan Kumar |  | 2024-05-17 |  |  |  | SS |  | 4 | 2024-05-17 | 2024-05-22 | 2024-05-17 | 2024-05-22 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 1 | 4 | T | Unit Test, Issues resolution | ESBCSE | Kolli Srinivas Rao |  | 2024-05-21 | 86 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 1 | 4 | T | Functional test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-05-22 | 87 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-05-22 | 2024-05-23 | 2024-05-22 | 2024-05-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 1 | 4 | T | Parallel test, Issues resolution | ESBCSE | Dhananjay Kumar |  | 2024-05-22 | 88 | ↖ | (T)Functio... | SS |  | 4 | 2024-05-22 | 2024-05-27 | 2024-05-22 | 2024-05-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 1 | 5 | T | Integration test, Issues resolution | ESBL | Sateesh Kumar |  | 2024-05-24 | 86 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-05-24 | 2024-05-29 | 2024-05-27 | 2024-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 1 | 6 | T | Documentation | BA | Kranthi Kumar |  | 2024-05-24 | 74 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-05-24 | 2024-05-30 | 2024-05-24 | 2024-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 1 | 2 | T | Sprint review | DL | Dilip Kumar |  | 2024-05-30 |  |  |  | SS |  | 1 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 1 | 3 | T | Sprint retrospective | EA | Steve Weiland |  | 2024-05-30 |  |  |  | SS |  | 1 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2024-05-30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 1 | -1 | S | Sprint 5 |  |  |  | 2024-05-31 |  |  |  | SS |  | 15 | 2024-05-31 | 2024-06-20 | 2024-05-31 | 2024-06-20 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 1 | -1 | T | Sprint planning/ Backlog Refinement |  |  |  | 2024-05-31 |  |  |  | SS |  | 1 | 2024-05-31 | 2024-05-31 | 2024-05-31 | 2024-05-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 1 | -1 | T | Application discovery (InvestmentGateway Bundle) |  |  |  | 2024-05-31 |  |  |  | SS |  | 3 | 2024-05-31 | 2024-06-04 | 2024-05-31 | 2024-06-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 1 | -1 | T | Define test cases |  |  |  | 2024-06-06 | 96 | ↖ | (T)Applica... | SS |  | 2 | 2024-06-06 | 2024-06-07 | 2024-06-05 | 2024-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 1 | -1 | T | Prepare test data |  |  |  | 2024-06-07 | 97 | ↖ | (T)Define ... | SS |  | 3 | 2024-06-07 | 2024-06-11 | 2024-06-07 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 1 | -1 | T | Upgrade Software |  |  |  | 2024-06-11 |  |  |  | SS |  | 4 | 2024-06-11 | 2024-06-14 | 2024-06-07 | 2024-06-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-06-12 | 99 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-06-12 | 2024-06-12 | 2024-06-11 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-06-12 | 100 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-06-12 | 101 | ↖ | (T)Functio... | SS |  | 4 | 2024-06-12 | 2024-06-17 | 2024-06-12 | 2024-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-06-17 | 99 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 1 | -1 | T | Application discovery (GlobalAccount Bundle) |  |  |  | 2024-05-31 |  |  |  | SS |  | 3 | 2024-05-31 | 2024-06-04 | 2024-05-31 | 2024-06-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 1 | -1 | T | Define test cases |  |  |  | 2024-06-05 | 104 | ↖ | (T)Applica... | SS |  | 2 | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 1 | -1 | T | Prepare test data |  |  |  | 2024-06-07 | 105 | ↖ | (T)Define ... | SS |  | 3 | 2024-06-07 | 2024-06-11 | 2024-06-07 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 1 | -1 | T | Upgrade Software |  |  |  | 2024-06-07 |  |  |  | SS |  | 4 | 2024-06-07 | 2024-06-12 | 2024-06-07 | 2024-06-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-06-07 | 107 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-06-07 | 2024-06-07 | 2024-06-11 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-06-11 | 108 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-06-11 | 2024-06-12 | 2024-06-12 | 2024-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-06-12 | 109 | ↖ | (T)Functio... | SS |  | 4 | 2024-06-12 | 2024-06-17 | 2024-06-12 | 2024-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-06-17 | 107 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 1 | -1 | T | Application discovery (UnitTrust Bundle) |  |  |  | 2024-05-31 |  |  |  | SS |  | 3 | 2024-05-31 | 2024-06-04 | 2024-05-31 | 2024-06-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 1 | -1 | T | Define test cases |  |  |  | 2024-06-05 | 112 | ↖ | (T)Applica... | SS |  | 2 | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 1 | -1 | T | Prepare test data |  |  |  | 2024-06-07 | 113 | ↖ | (T)Define ... | SS |  | 3 | 2024-06-07 | 2024-06-11 | 2024-06-07 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 1 | -1 | T | Upgrade Software |  |  |  | 2024-06-07 |  |  |  | SS |  | 4 | 2024-06-07 | 2024-06-12 | 2024-06-07 | 2024-06-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-06-11 | 115 | ↖ | (T)Upgrade... | SS |  | 2 | 2024-06-11 | 2024-06-12 | 2024-06-11 | 2024-06-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-06-12 | 116 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-06-12 | 2024-06-13 | 2024-06-12 | 2024-06-13 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-06-12 | 117 | ↖ | (T)Functio... | SS |  | 4 | 2024-06-12 | 2024-06-17 | 2024-06-12 | 2024-06-17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-06-17 | 115 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 1 | -1 | T | Documentation |  |  |  | 2024-06-14 | 95 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-06-14 | 2024-06-20 | 2024-06-14 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 1 | -1 | T | Sprint review |  |  |  | 2024-06-20 |  |  |  | SS |  | 1 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 1 | -1 | T | Sprint retrospective |  |  |  | 2024-06-20 |  |  |  | SS |  | 1 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 1 | -1 | S | Sprint 6 |  |  |  | 2024-06-05 |  |  |  | SS |  | 42 | 2024-06-05 | 2024-08-01 | 2024-06-21 | 2024-07-11 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 1 | -1 | T | Sprint planning/ Backlog Refinement |  |  |  | 2024-06-21 |  |  |  | SS |  | 1 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-06-21 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 1 | -1 | T | Application discovery (Bill Payment Bundle) |  |  |  | 2024-06-21 |  |  |  | SS |  | 3 | 2024-06-21 | 2024-06-25 | 2024-06-21 | 2024-06-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 1 | -1 | T | Define test cases |  |  |  | 2024-06-26 | 125 | ↖ | (T)Applica... | SS |  | 2 | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 1 | -1 | T | Prepare test data |  |  |  | 2024-06-26 | 126 | ↖ | (T)Define ... | SS |  | 3 | 2024-06-26 | 2024-06-28 | 2024-06-28 | 2024-07-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 1 | -1 | T | Upgrade Software |  |  |  | 2024-06-28 |  |  |  | SS |  | 4 | 2024-06-28 | 2024-07-03 | 2024-06-28 | 2024-07-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-06-28 | 128 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-06-28 | 2024-06-28 | 2024-07-02 | 2024-07-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-06-28 | 129 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-06-28 | 2024-07-01 | 2024-07-03 | 2024-07-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-07-03 | 130 | ↖ | (T)Functio... | SS |  | 4 | 2024-07-03 | 2024-07-08 | 2024-07-03 | 2024-07-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-07-08 | 128 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-07-08 | 2024-07-11 | 2024-07-08 | 2024-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 1 | -1 | T | Application discovery (RateService Bundle) |  |  |  | 2024-06-21 |  |  |  | SS |  | 3 | 2024-06-21 | 2024-06-25 | 2024-06-21 | 2024-06-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 1 | -1 | T | Define test cases |  |  |  | 2024-06-26 | 133 | ↖ | (T)Applica... | SS |  | 2 | 2024-06-26 | 2024-06-27 | 2024-06-26 | 2024-06-27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 1 | -1 | T | Prepare test data |  |  |  | 2024-06-28 | 134 | ↖ | (T)Define ... | SS |  | 3 | 2024-06-28 | 2024-07-02 | 2024-06-28 | 2024-07-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 1 | -1 | T | Upgrade software |  |  |  | 2024-06-28 |  |  |  | SS |  | 4 | 2024-06-28 | 2024-07-03 | 2024-06-28 | 2024-07-03 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-07-02 | 136 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-07-02 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-07-03 | 137 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-04 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-07-08 | 138 | ↖ | (T)Functio... | SS |  | 4 | 2024-07-08 | 2024-07-11 | 2024-07-03 | 2024-07-08 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-07-08 | 139 | ↖ | (T)Paralle... | SS |  | 4 | 2024-07-08 | 2024-07-11 | 2024-07-08 | 2024-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 1 | -1 | T | Documentation |  |  |  | 2024-06-05 | 124 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-06-05 | 2024-06-11 | 2024-07-05 | 2024-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 1 | -1 | T | Sprint review |  |  |  | 2024-07-11 |  |  |  | SS |  | 1 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 1 | -1 | T | Sprint retrospective |  |  |  | 2024-07-11 |  |  |  | SS |  | 1 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 1 | -1 | S | Sprint 7 |  |  |  | 2024-07-12 |  |  |  | SS |  | 15 | 2024-07-12 | 2024-08-01 | 2024-07-12 | 2024-08-01 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 1 | -1 | T | Sprint planning/ Backlog Refinement |  |  |  | 2024-07-12 |  |  |  | SS |  | 1 | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-12 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 1 | -1 | T | Application discovery (ATMDataXFer Bundle) |  |  |  | 2024-07-12 |  |  |  | SS |  | 3 | 2024-07-12 | 2024-07-16 | 2024-07-12 | 2024-07-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 1 | -1 | T | Define test cases |  |  |  | 2024-07-17 | 146 | ↖ | (T)Applica... | SS |  | 2 | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 1 | -1 | T | Prepare test data |  |  |  | 2024-07-19 | 147 | ↖ | (T)Define ... | SS |  | 3 | 2024-07-19 | 2024-07-23 | 2024-07-19 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 1 | -1 | T | Upgrade software |  |  |  | 2024-07-19 |  |  |  | SS |  | 4 | 2024-07-19 | 2024-07-24 | 2024-07-19 | 2024-07-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-07-23 | 149 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-07-24 | 150 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-07-24 | 151 | ↖ | (T)Functio... | SS |  | 4 | 2024-07-24 | 2024-07-29 | 2024-07-24 | 2024-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-07-12 | 149 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-07-12 | 2024-07-17 | 2024-07-29 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 1 | -1 | T | Application discovery (UniversalCustomer Bundle) |  |  |  | 2024-07-12 |  |  |  | SS |  | 3 | 2024-07-12 | 2024-07-16 | 2024-07-12 | 2024-07-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 1 | -1 | T | Define test cases |  |  |  | 2024-07-19 | 154 | ↖ | (T)Applica... | SS |  | 2 | 2024-07-19 | 2024-07-22 | 2024-07-17 | 2024-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 1 | -1 | T | Prepare test data |  |  |  | 2024-07-19 | 155 | ↖ | (T)Define ... | SS |  | 3 | 2024-07-19 | 2024-07-23 | 2024-07-19 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 1 | -1 | T | Upgrade software |  |  |  | 2024-07-19 |  |  |  | SS |  | 4 | 2024-07-19 | 2024-07-24 | 2024-07-19 | 2024-07-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-07-23 | 157 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-07-24 | 158 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-07-25 | 159 | ↖ | (T)Functio... | SS |  | 4 | 2024-07-25 | 2024-07-30 | 2024-07-24 | 2024-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-07-24 | 160 | ↖ | (T)Paralle... | SS |  | 4 | 2024-07-24 | 2024-07-29 | 2024-07-29 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 1 | -1 | T | Application discovery (MoneyLine Core Bundle) |  |  |  | 2024-07-29 |  |  |  | SS |  | 3 | 2024-07-29 | 2024-07-31 | 2024-07-12 | 2024-07-16 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 1 | -1 | T | Define test cases |  |  |  | 2024-07-12 | 163 | ↙ | (T)Define ... | SS |  | 2 | 2024-07-12 | 2024-07-15 | 2024-07-17 | 2024-07-18 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 1 | -1 | T | Prepare test data |  |  |  | 2024-07-19 | 164 | ↙ | (T)Prepare... | SS |  | 3 | 2024-07-19 | 2024-07-23 | 2024-07-19 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 1 | -1 | T | Upgrade software |  |  |  | 2024-07-19 |  |  |  | SS |  | 4 | 2024-07-19 | 2024-07-24 | 2024-07-19 | 2024-07-24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 1 | -1 | T | Unit Test, Issues resolution |  |  |  | 2024-07-23 | 165 | ↖ | (T)Upgrade... | SS |  | 1 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2024-07-23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 1 | -1 | T | Functional test, Issues resolution |  |  |  | 2024-07-23 | 166 | ↖ | (T)Unit Te... | SS |  | 2 | 2024-07-23 | 2024-07-24 | 2024-07-24 | 2024-07-25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 1 | -1 | T | Parallel test, Issues resolution |  |  |  | 2024-07-24 | 167 | ↖ | (T)Functio... | SS |  | 4 | 2024-07-24 | 2024-07-29 | 2024-07-24 | 2024-07-29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 1 | -1 | T | Integration test, Issues resolution |  |  |  | 2024-07-29 | 165 | ↖ | (T)Upgrade... | SS |  | 4 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 1 | -1 | T | Documentation |  |  |  | 2024-07-26 | 145 | ↖ | (T)Sprint ... | SS |  | 5 | 2024-07-26 | 2024-08-01 | 2024-07-26 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 1 | -1 | T | Sprint review |  |  |  | 2024-08-01 |  |  |  | SS |  | 1 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 1 | -1 | T | Sprint retrospective |  |  |  | 2024-08-01 |  |  |  | SS |  | 1 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 1 | -1 | S | Sprint 8 |  |  |  | 2024-08-02 |  |  |  | SS |  | 6 | 2024-08-02 | 2024-08-09 | 2024-08-02 | 2024-08-09 | 17.91% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 1 | -1 | T | Sprint planning/ Backlog Refinement |  |  |  | 2024-08-02 |  |  |  | SS |  | 1 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 12% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 1 | -1 | T | Technical Reference Document |  |  |  | 2024-08-02 | 4 | ↖ | (T)Archite... | SS |  | 5 | 2024-08-02 | 2024-08-08 | 2024-08-02 | 2024-08-08 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 1 | -1 | T | Upgraded production build |  |  |  | 2024-08-02 | 6 | ↖ | (T)Review ... | SS |  | 5 | 2024-08-02 | 2024-08-08 | 2024-08-02 | 2024-08-08 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 1 | -1 | T | Release Notes document |  |  |  | 2024-08-02 | 16 | ↖ | (T)Side by... | SS |  | 5 | 2024-08-02 | 2024-08-08 | 2024-08-02 | 2024-08-08 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 1 | -1 | T | Operational Documentation |  |  |  | 2024-08-02 | 3 | ↖ | (T)Documen... | SS |  | 5 | 2024-08-02 | 2024-08-08 | 2024-08-02 | 2024-08-08 | 20% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 1 | -1 | T | Sprint review |  |  |  | 2024-08-09 |  |  |  | SS |  | 1 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 1 | -1 | T | Sprint retrospective |  |  |  | 2024-08-09 |  |  |  | SS |  | 1 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on R13: Efforts (Days)

## WBS - Impediments
Code | Level1 | Level2 | Level3 | Level4 | Level5 | Concatenate | Count | Subtitute | Find | Code | Final | Duration (hr) | Resources | Task Description | Dependency Nature | Technically assess and validate the capabilities as provided by the platform vendor
Sprint1.0 | 1 | 0 |  |  |  | 1.0.... | 2 | 1.0?... | 4 | 1.0 | 1.0 | 10 |  | Discovery | Low | Transition code to production libraries and setup change management and maintainence plans
Sprint1.1 | 1 | 1 | 0 |  |  | 1.1.0... | 3 | 1.1.0?.. | 6 | 1.1.0 | 1.1 |  |  | Document current APIs |  | Documentation library setup and reception by JMMB
Sprint1.1.1 | 1 | 1 | 1 | 0 |  | 1.1.1.0.. | 4 | 1.1.1.0?. | 8 | 1.1.1.0 | 1.1.1 | 4 | BA , SE | Architecture Design Document Template |  | Setup monitoring services and reporitng processes
Sprint1.2 | 1 | 2 | 0 |  |  | 1.2.0... | 3 | 1.2.0?.. | 6 | 1.2.0 | 1.2 | 5 | SE,ESBL,TSTL | Review production environment |  | Test connectivity with ESB
Sprint1.3 | 1 | 3 | 0 |  |  | 1.3.0... | 3 | 1.3.0?.. | 6 | 1.3.0 | 1.3 | 2 | ESBL,SE,IA | Build Dev and Test environments |  | Execute software and hardware upgrade
Sprint1.4 | 1 | 4 | 0 |  |  | 1.4.0... | 3 | 1.4.0?.. | 6 | 1.4.0 | 1.4 | 3 | JMMB Infrastructure,IA | Build Disater Environment |  | Test migration plan
Sprint1.5 | 1 | 5 | 0 |  |  | 1.5.0... | 3 | 1.5.0?.. | 6 | 1.5.0 | 1.5 |  |  | KT/Understand flow of existing environment |  | Create Migration services plan (by bundles)
Sprint1.5.1 | 1 | 5 | 1 | 0 |  | 1.5.1.0.. | 4 | 1.5.1.0?. | 8 | 1.5.1.0 | 1.5.1 | 4 | Consultant ESB | Side by side version comparison |  | Build production serviers
Sprint2.0 | 2 | 0 |  |  |  | 2.0.... | 2 | 2.0?... | 4 | 2.0 | 2.0 |  |  | Design |  | Build and run performance tests
Sprint2.1 | 2 | 1 | 0 |  |  | 2.1.0... | 3 | 2.1.0?.. | 6 | 2.1.0 | 2.1 | 45 | ESBL,IA | Build EA view of interface architecture |  | Build and run regression test to validate gaps and upgrade features
Sprint2.2 | 2 | 2 | 0 |  |  | 2.2.0... | 3 | 2.2.0?.. | 6 | 2.2.0 | 2.2 | 2 | JMMB EA & ESB Architect | Review ESB Architecture Design |  | Perform unit and system test
Sprint2.3 | 2 | 3 | 0 |  |  | 2.3.0... | 3 | 2.3.0?.. | 6 | 2.3.0 | 2.3 | 10 | ESBL,IA | Build Interface Architecture Design |  | Build and test rollback plan
Sprint2.4 | 2 | 4 | 0 |  |  | 2.4.0... | 3 | 2.4.0?.. | 6 | 2.4.0 | 2.4 | 10 | ESBL,JMMB EA | Build API policies and standards |  | Build test, deployment, and certification plan
Sprint2.5 | 2 | 5 | 0 |  |  | 2.5.0... | 3 | 2.5.0?.. | 6 | 2.5.0 | 2.5 | 10 | ESBL,IA,JMMB EA,TSTL | Design/Select migration tools |  | Configure and change any interface code or bundle
Sprint2.6 | 2 | 6 | 0 |  |  | 2.6.0... | 3 | 2.6.0?.. | 6 | 2.6.0 | 2.6 | 10 | JMMB EA | Code and Tech review |  | Change code and perform review
Sprint2.7 | 2 | 7 | 0 |  |  | 2.7.0... | 3 | 2.7.0?.. | 6 | 2.7.0 | 2.7 | 3 | ESBL,IA,JMMB EA & Infrastructure,SE | Design & build roll back process |  | Stage software for changes
Sprint2.8 | 2 | 8 | 0 |  |  | 2.8.0... | 3 | 2.8.0?.. | 6 | 2.8.0 | 2.8 |  |  | Design and Build Failover Process |  | Design changes to software and config specs
Sprint2.9 | 2 | 9 | 0 |  |  | 2.9.0... | 3 | 2.9.0?.. | 6 | 2.9.0 | 2.9 |  |  | Integration Logging code/Tools |  | Build Gap analysis report
Sprint3.0 | 3 | 0 |  |  |  | 3.0.... | 2 | 3.0?... | 4 | 3.0 | 3.0 | 123 |  | Test |  | Review Apache Upgrade Information
Sprint3.1 | 3 | 1 | 0 |  |  | 3.1.0... | 3 | 3.1.0?.. | 6 | 3.1.0 | 3.1 | 3 | JMMB Infrastructure ,IA ,TSTL | Build Test environments |  | Review Apache Upgrade code
Sprint3.2 | 3 | 2 | 0 |  |  | 3.2.0... | 3 | 3.2.0?.. | 6 | 3.2.0 | 3.2 | 2 | JMMB Infrastructure | Install v 7 |  | REview current software code
Sprint3.3 | 3 | 3 | 0 |  |  | 3.3.0... | 3 | 3.3.0?.. | 6 | 3.3.0 | 3.3 | 3 | JMMB Security | Setup security services |  | Refine and publish project plan (Design and Gap Analysis)
Sprint3.4 | 3 | 4 | 0 |  |  | 3.4.0... | 3 | 3.4.0?.. | 6 | 3.4.0 | 3.4 | 3 | TE,TSTL | Batch 1 - Run performance tests |  | Prepare test scenarios and data
Sprint3.5 | 3 | 5 | 0 |  |  | 3.5.0... | 3 | 3.5.0?.. | 6 | 3.5.0 | 3.5 | 15 | JMMB QA | Batch 1 - Run QA |  | To evaluate the upgrade differences
Sprint3.6 | 3 | 6 | 0 |  |  | 3.6.0... | 3 | 3.6.0?.. | 6 | 3.6.0 | 3.6 | 15 | JMMB UAT | Batch 1 - Run UAT |  | To manage conversion changes, supporting the migration and testing effors
Sprint3.7 | 3 | 7 | 0 |  |  | 3.7.0... | 3 | 3.7.0?.. | 6 | 3.7.0 | 3.7 | 3 | IA,TE,TSTL | Batch 1 - Test roll back process |  | To support configuration and desing activities + Detailed Technical Design + Support Testing and development
Sprint3.8 | 3 | 8 | 0 |  |  | 3.8.0... | 3 | 3.8.0?.. | 6 | 3.8.0 | 3.8 | 3 | TE,TSTL | Batch 2 - Run performance tests |  | Activities within the ESB Upgrade (ESB Architect/Tech Lead)
Sprint3.9 | 3 | 9 | 0 |  |  | 3.9.0... | 3 | 3.9.0?.. | 6 | 3.9.0 | 3.9 | 15 | JMMB QA | Batch 2 - Run QA |  | Report the status of project to JMMB sponsors (Director Lead)
Sprint3.10 | 3 | 10 | 0 |  |  | 3.10.0... | 3 | 3.10.0?.. | 7 | 3.10.0 | 3.10 | 15 | JMMB UAT | Batch 2 - Run UAT |  | Ensure strategic direction and optimum quality of deliverables (delivery director)
Sprint3.11 | 3 | 11 | 0 |  |  | 3.11.0... | 3 | 3.11.0?.. | 7 | 3.11.0 | 3.11 | 3 | IA,TE,TSTL | Batch 2 - Test roll back process |  | Review, upgrade and evaluate ESB
Sprint3.12 | 3 | 12 | 0 |  |  | 3.12.0... | 3 | 3.12.0?.. | 7 | 3.12.0 | 3.12 | 3 | TE,TSTL | Batch 3 - Run performance tests |  | Necessary system access
Sprint3.13 | 3 | 13 | 0 |  |  | 3.13.0... | 3 | 3.13.0?.. | 7 | 3.13.0 | 3.13 | 20 | JMMB QA | Batch 3 - Run QA |  | Hardware/Software work area, for IGT Consultants
Sprint3.14 | 3 | 14 | 0 |  |  | 3.14.0... | 3 | 3.14.0?.. | 7 | 3.14.0 | 3.14 | 20 | JMMB UAT | Batch 3 – Run UAT |  | Be responsible for Secuirty certification
Sprint3.15 | 3 | 15 | 0 |  |  | 3.15.0... | 3 | 3.15.0?.. | 7 | 3.15.0 | 3.15 | 3 | IA,TE,TSTL | Batch 3 - Test roll back process |  | Information Secuirty of ESB Services
Sprint3.16 | 3 | 16 | 0 |  |  | 3.16.0... | 3 | 3.16.0?.. | 7 | 3.16.0 | 3.16 |  |  |  |  | be responsible for migrating source code to upper environments and all other configuraiton management, test data management
Sprint4.0 | 4 | 0 |  |  |  | 4.0.... | 2 | 4.0?... | 4 | 4.0 | 4.0 | 57 |  | Deploy |  | be responsible for compalince of legal requirements
Sprint4.1 | 4 | 1 | 0 |  |  | 4.1.0... | 3 | 4.1.0?.. | 6 | 4.1.0 | 4.1 | 1 | ESBL,IA,SE | Setup Migration tools | Medium | Be responsible for the quality assurance, user acceptance, end-to-end perforamnce and load testing of ESB Services prior to production release.
Sprint4.2 | 4 | 2 | 0 |  |  | 4.2.0... | 3 | 4.2.0?.. | 6 | 4.2.0 | 4.2 | 1 | ESBL,IA,SE | Migrate Bundle Batch 1 |  | manage the functional certification of the certification of the interface services after the upgrade and migration of the platform to ensure application performs as expected nased on updated version
Sprint4.3 | 4 | 3 | 0 |  |  | 4.3.0... | 3 | 4.3.0?.. | 6 | 4.3.0 | 4.3 | 1 | ESBL,IA,SE,TE,TSTL,JMMB Infrastructure | Check and test |  | be responible for provisioning of environments and their maintainece management and monitoring during the project
Sprint4.4 | 4 | 4 | 0 |  |  | 4.4.0... | 3 | 4.4.0?.. | 6 | 4.4.0 | 4.4 | 7 | JMMB Infrastructure Monitoring | Time to Validate Performance in Production |  | be fixing code changes of bugs introduced by the upgrade development
Sprint4.5 | 4 | 5 | 0 |  |  | 4.5.0... | 3 | 4.5.0?.. | 6 | 4.5.0 | 4.5 | 2 | ESBL,IA,SE | Migrate Bundle Batch 2 |  | Fixing of bugs introduced by the ugrade development
Sprint4.6 | 4 | 6 | 0 |  |  | 4.6.0... | 3 | 4.6.0?.. | 6 | 4.6.0 | 4.6 | 1 | ESBL,IA,SE,TE,TSTL,JMMB Infrastructure | Check and test
Sprint4.7 | 4 | 7 | 0 |  |  | 4.7.0... | 3 | 4.7.0?.. | 6 | 4.7.0 | 4.7 | 7 | JMMB Infrastructure Monitoring | Time to Validate Performance in Production
Sprint4.8 | 4 | 8 | 0 |  |  | 4.8.0... | 3 | 4.8.0?.. | 6 | 4.8.0 | 4.8 | 2 | ESBL,IA,SE | Migrate Bundle Batch 3
Sprint4.9 | 4 | 9 | 0 |  |  | 4.9.0... | 3 | 4.9.0?.. | 6 | 4.9.0 | 4.9 | 1 | ESBL,IA,SE,TE,TSTL,JMMB Infrastructure | Check and test
Sprint4.10 | 4 | 10 | 0 |  |  | 4.10.0... | 3 | 4.10.0?.. | 7 | 4.10.0 | 4.10 | 2 | ESBL,JMMB,TE,TSTL | Certify environment
Sprint4.11 | 4 | 11 | 0 |  |  | 4.11.0... | 3 | 4.11.0?.. | 7 | 4.11.0 | 4.11 | 1 | JMMB | Initiate production services
Sprint4.12 | 4 | 12 | 0 |  |  | 4.12.0... | 3 | 4.12.0?.. | 7 | 4.12.0 | 4.12 | 30 | ESBL,IA,SE,JMMB | Post implementation monitoring
Sprint4.13 | 4 | 13 | 0 |  |  | 4.13.0... | 3 | 4.13.0?.. | 7 | 4.13.0 | 4.13 | 1 | ESBL,JMMB | Project sign off
Sprint5.0 | 5 | 0 |  |  |  | 5.0.... | 2 | 5.0?... | 4 | 5.0 | 5.0 |  |  | Architectural Documention
Sprint6.0 | 6 | 0 |  |  |  | 6.0.... | 2 | 6.0?... | 4 | 6.0 | 6.0 |  |  | Software Documention
Sprint7.0 | 7 | 0 |  |  |  | 7.0.... | 2 | 7.0?... | 4 | 7.0 | 7.0 |  |  | operational Documention
operational Documention
Note on O9: Version 4, 5, 6, 7 config parameters check